## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Akshaya B | 16-02-2026 | Retrieved document chunks were not always relevant for certain user queries | Sprint 2 | Self | Logical | YES | 18-02-2026 | Closed | Retrieval relevance improved
2 | Akshaya B | 23-02-2026 | Generated answers did not include proper source citations for some responses | Sprint 3 | Self | Standards | YES | 25-02-2026 | Closed | Citation issue resolved
3 | Akshaya B | 2026-01-03 | Chat history was not properly considered for follow-up questions | Sprint 3 | Self | Logical | YES | 2026-03-03 | Closed | Context handling improved
4 | Akshaya B | 2026-05-03 | UI was not updating after new messages were added | Sprint 2 | Self | User Interface | YES | 15-03-2026 | Closed | UI updates working correctly
5 | Akshaya B | 28-03-2026 | System failed when uploading multiple documents simultaneously | Sprint 3 | Self | Standards | YES | 30-03-2026 | Closed | Multiple uploads handled properly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others